## Sheet1
Metatron Launch and Pilot Plan	v.0.1
		Prep	Sprint 1: Protocol				Sprint 2: UX				Sprint 3: Launch				Sprint 4: Pilot			Sprint 5: Sustaining
Activity	Assignee	Wk1	Wk2	Wk3	Wk4	Wk5	Wk6	Wk7	Wk8	Wk9	Wk10	Wk11	Wk12	Wk13	Wk14	Wk15	Wk16	Wk17	Wk18	Wk19	Wk20
Overall Project Management & Lead	flaxscrip	5	5	5	5	5	5	5	5	5	5	5	5
Nomicon Launch & Operations	macterra	5	5				5				5			5			5				5
IT Setup – repo, host, emails	flaxscrip	10				5				5				5			5				5
Metatron Docs – Installation	flaxscrip	5	5				5				5					5
Metatron Docs – Getting Started	flaxscrip		5					5				5					5
Metatron Docs – Contrib, License, etc	flaxscrip			5
Metatron Docs – Dev Architecture	aiggdev	10
Metatron Docs – Architecture Docs Updates	flaxscrip			5	5			5	5					5	5
Metatron Docs – Dev Testing	aiggdev	5
Metatron Docs – Requirements	flaxscrip	5				5				5
Metatron Docs – Sample Use Cases (EDEN)	flaxscrip	5			5	5	5	5	5	5	5
Code Review	macterra		5	5	5	5	5	5	5	5
Code Review	flaxscrip	5				5
Code Review	aiggdev	5	5	5	5	5	5	5	5
Code Review	filecoin-tbd	15	10	5	5	5	5	5	5	5	5
Release Candidate Scope Definition	flaxscrip	5
Identify Features Gap	macterra	5				5				5
Define new Filecoin integration	filecoin-tbd	5	10	15	15	15
Design and Architecture Support	macterra			5	5			5	5			5	5
Design & Implement Protocol Changes	aiggdev		15	15	15	15
Define & Document Environment Config	flaxscrip		10	10	10
Launch Development Environment	flaxscrip		15	10	5
Design and Implement UX Changes	aiggdev					15	15	15	15
Design and Implement minimal Filecoin integ.	filecoin-tbd					15	15	15	15
Configure Metatron Data Types	flaxscrip					5		5
Prepare Code for Release	aiggdev					15
Prepare Git Repo	flaxscrip					5
Prepare Docker Release	aiggdev					15
Prepare EDEN Instance	flaxscrip					5
Prepare Filecoin/IPFS for EDEN	filecoin-tbd					15	15	15	15
Finalize Release Docs and Code	aiggdev					15	15
Engage with 3 EDA Pilot Candidates	flaxscrip					5	5	5	5	5
Implement Pilot Use Cases	flaxscrip					5	5	5	5	5	5	5
Support Pilot Nodes	aiggdev					15	15	15	15	10	10	5
Deploy and Support Filecoin nodes	filecoin-tbd					15	15	15	15	10	10	5
Train Pilot Candidates	flaxscrip					5
Prepare Pilot Demonstration	flaxscrip
Support Pilot Nodes	flaxscrip
EDA Community Launch & Coordination	flaxscrip			5	5	5	5	5	5	5	10	10	10	10	10	5	5	5	5	5	5

Resources
	flaxscrip	40	40	40	35	30	25	25	25	25	25	25	25	25	25	25	25	25	25	15	20	545
	filecoin-tbd	20	20	20	20	20	20	20	20	20	20	20	20	20	20	20	20	20	15	15	10	380
	aiggdev	20	20	20	20	20	20	20	20	20	20	20	20	20	20	20	20	15	10	10	5	360
	macterra	10	10	10	10	10	10	10	10	10	10	10	10	10	5	5	10	0	0	0	5	155
Deliverables						1440
Github Repo README.md	1
Nomicon Collaboration Space	2
Filecoin Use Cases and Designs	3
Development Environment Available	4
Metatron Documentation	5
Metatron Protocol RC 1	6
Filecoin Integration RC 1	7
Initial Metatron Data Types	8
Metatron UX RC 1	9
Metatron Repo RC 1	10
Metatron Docker – RC 1	11
Metatron & Filecoin EDEN Pilot Servers	12
Launch EDA Pilot Group	13
Public Technology Pilot	14
Postmortem Support	15
Presentation for Global Promotion	16